## Dashboard
YOUNG AND SAFE PROJECT
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
Number of Activities Done
36%
Activities Completed by Project Pillar
Youth Reached
Outsatnding Activities
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Data
YEAR | PILLAR | ACTIVITY | TARGET | ACTUAL TARGET | OUTSTANDING | STATUS | COVERAGE | ACTUAL COVERAGE | DIFF
2023 | PILLAR 1 | Youth Well being Report | 1 | 1 | 0 | Complete | 500 | 200 | 300
2023 | PILLAR 1 | Youth Advocacy | 3 | 3 | 0 | Complete | 500 | 200 | 300
2023 | PILLAR 1 | Y-Radio Show | 5 | 5 | 0 | Complete | 300 | 200 | 100
2023 | PILLAR 2 | Mental health | 5 | 4 | 1 | Pending | 400 | 200 | 200
2023 | PILLAR 2 | Sexual Reproductive | 5 | 2 | 3 | Pending | 200 | 200 | 0
2023 | PILLAR 2 | Cyber Hygeine | 4 | 1 | 3 | Pending | 100 | 200 | -100
2023 | PILLAR 3 | Design Thinking | 3 | 2 | 1 | Pending | 100 | 200 | -100
2023 | PILLAR 3 | Ho creative talent | 5 | 2 | 3 | Pending | 200 | 200 | 0
2023 | PILLAR 3 | Redevelopment of Park | 1 | 1 | 0 | Complete | 300 | 200 | 100
2023 | PILLAR 4 | NodeX | 4 | 3 | 1 | Pending | 200 | 200 | 0
2023 | PILLAR 4 | Virtaul Reality | 4 | 3 | 1 | Pending | 300 | 200 | 100
2024 | PILLAR 1 | Youth Well being Report | 1 | 1 | 0 | Complete | 500 | 200 | 300
2024 | PILLAR 1 | Youth Advocacy | 3 | 3 | 0 | Complete | 500 | 200 | 300
2024 | PILLAR 1 | Y-Radio Show | 5 | 5 | 0 | Complete | 300 | 200 | 100
2024 | PILLAR 2 | Mental health | 5 | 4 | 1 | Pending | 400 | 200 | 200
2024 | PILLAR 2 | Sexual Reproductive | 5 | 2 | 3 | Pending | 200 | 200 | 0
2024 | PILLAR 2 | Cyber Hygeine | 4 | 1 | 3 | Pending | 100 | 200 | -100
2024 | PILLAR 3 | Design Thinking | 3 | 2 | 1 | Pending | 100 | 200 | -100
2024 | PILLAR 3 | Ho creative talent | 5 | 2 | 3 | Pending | 200 | 200 | 0
2024 | PILLAR 3 | Redevelopment of Park | 1 | 1 | 0 | Complete | 300 | 200 | 100
2024 | PILLAR 4 | NodeX | 4 | 3 | 1 | Pending | 200 | 200 | 0
2024 | PILLAR 4 | Virtaul Reality | 4 | 3 | 1 | Pending | 300 | 200 | 100
2025 | PILLAR 1 | Youth Well being Report | 1 | 1 | 0 | Complete | 500 | 200 | 300
2025 | PILLAR 1 | Youth Advocacy | 3 | 3 | 0 | Complete | 500 | 200 | 300
2025 | PILLAR 1 | Y-Radio Show | 5 | 5 | 0 | Complete | 300 | 200 | 100
2025 | PILLAR 2 | Mental health | 5 | 4 | 1 | Pending | 400 | 200 | 200
2025 | PILLAR 2 | Sexual Reproductive | 5 | 2 | 3 | Pending | 200 | 200 | 0
2025 | PILLAR 2 | Cyber Hygeine | 4 | 1 | 3 | Pending | 100 | 200 | -100
2025 | PILLAR 3 | Design Thinking | 3 | 2 | 1 | Pending | 100 | 200 | -100
2025 | PILLAR 3 | Ho creative talent | 5 | 2 | 3 | Pending | 200 | 200 | 0
2025 | PILLAR 3 | Redevelopment of Park | 1 | 1 | 0 | Complete | 300 | 200 | 100
2025 | PILLAR 4 | NodeX | 4 | 3 | 1 | Pending | 200 | 200 | 0
2025 | PILLAR 4 | Virtaul Reality | 4 | 3 | 1 | Pending | 300 | 200 | 100

## Charts
Row Labels | TARGET NUMBER OF YOUTH | ACTUAL NUMBER OF YOUTH
2023 | 3100 | 2200
PILLAR 1 | 1300 | 600
PILLAR 2 | 700 | 600
PILLAR 3 | 600 | 600
PILLAR 4 | 500 | 400
2024 | 3100 | 2200
PILLAR 1 | 1300 | 600
PILLAR 2 | 700 | 600
PILLAR 3 | 600 | 600
PILLAR 4 | 500 | 400
2025 | 3100 | 2200
PILLAR 1 | 1300 | 600
PILLAR 2 | 700 | 600
PILLAR 3 | 600 | 600
PILLAR 4 | 500 | 400
Grand Total | 9300 | 6600
Row Labels | Count of STATUS
Complete | 12 | 36.36%
Pending | 21
Grand Total | 33
| Row Labels | NUMBER OF ACTIVITIES
| Cyber Hygeine | 3 | Advocacy | 9
| Design Thinking | 6 | Well being Report | 3
| Ho creative talent | 6 | Y-Radio Show | 15
| Mental health | 12 | Mental health | 12
| NodeX | 9 | SRH Bootcamp | 6
| Redevelopment of Park | 3 | Cyber Hygeine | 3
| Sexual Reproductive | 6 | Design Thinking | 6
| Virtaul Reality | 9 | Ho creative talent | 6
| Youth Advocacy | 9 | Redevelopment of Park | 3
| Youth Well being Report | 3 | NodeX | 9
| Y-Radio Show | 15 | Virtaul Reality | 9
| Grand Total | 81 | Total | 81
Row Labels | TARGET No. | OUTSTANDING No.
Cyber Hygeine | 12 | 9
Design Thinking | 9 | 3
Ho creative talent | 15 | 9
Mental health | 15 | 3
NodeX | 12 | 3
Redevelopment of Park | 3 | 0
Sexual Reproductive | 15 | 9
Virtaul Reality | 12 | 3
Youth Advocacy | 9 | 0
Youth Well being Report | 3 | 0
Y-Radio Show | 15 | 0
Grand Total | 120 | 39
36%
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.